TECHNICAL DOCUMENTATION

TailWag App: Render Migration

From Static Site to Full-Stack Web Application

4-Day Sprint  |  March 26–29, 2026

Prepared for: Summer Wright, Founder

Domain: usetailwag.co

GitHub Repo: swc2126/usetailwag.co

Last Updated: March 26, 2026

# Contents

1. Project Overview

2. Architecture Decision: Why Render + Supabase

3. Technology Stack

4. 4-Day Sprint Plan

5. Phase 1: Scaffold & Infrastructure (Day 1)

6. Phase 2: Auth & Payments (Day 2)

7. Phase 3: Dashboard & Polish (Day 3)

8. Phase 4: Domain Migration & Go-Live (Day 4)

9. Troubleshooting Guide

10. Post-Launch Checklist

11. Change Log

# 1. Project Overview

TailWag is migrating from a static GitHub Pages marketing site to a full-stack web application hosted on Render. This migration enables user authentication, Stripe payment processing, database-backed user management, and a post-login dashboard — capabilities that are impossible on a static hosting platform.

What’s changing:

- Current state: Static HTML site on GitHub Pages (usetailwag.co) with no backend

- Target state: Node.js + Express app on Render with Supabase auth/database, Stripe payments, and a user dashboard

- Timeline: 4 days (March 26–29, 2026)

- Zero-downtime migration: Build on staging URL, then switch DNS when ready

What’s NOT changing:

- All code stays in GitHub (Render deploys from the repo automatically)

- The marketing site design and content remain the same

- The domain (usetailwag.co) stays the same — visitors won’t notice a difference

# 2. Architecture Decision: Why Render + Supabase

Two key decisions were made before starting this sprint:

### Why not stay on GitHub Pages?

GitHub Pages is a static file host. It can serve HTML, CSS, and JavaScript but cannot run server-side code, connect to a database, or process payments securely. TailWag needs all three to support user accounts, Stripe subscriptions, and a dashboard. GitHub Pages remains an excellent choice for the marketing site alone, but a SaaS product requires a real backend.

### Why Render?

Render offers managed hosting that deploys directly from a GitHub repository. Every push to the main branch triggers an automatic redeploy. It supports Node.js natively, offers managed PostgreSQL databases, free SSL, and custom domain configuration. For a startup at TailWag’s stage, it provides the right balance of simplicity, scalability, and cost (free tier available for initial setup).

### Why Supabase?

Building user authentication from scratch (password hashing, session management, token refresh, password reset emails) would take 1–2 days alone. Supabase provides production-ready authentication out of the box, plus a PostgreSQL database with a visual dashboard for managing data. It’s free at TailWag’s scale and used by thousands of startups. This decision saved approximately 2 days on a 4-day sprint.

# 3. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend |  | Existing HTML/CSS/JS pages (marketing, login, signup) |
| Backend | Node.js + Express | API routes, Stripe webhooks, page serving |
| Auth | Supabase Auth | User signup, login, sessions, password reset |
| Database | Supabase PostgreSQL | Users, daycares, subscriptions, settings |
| Payments | Stripe Checkout | Hosted payment page for plan subscriptions |
| Hosting | Render | Web service with auto-deploy from GitHub |
| DNS | Namecheap | Domain management, A records / CNAME |
| Code Repo | GitHub | Source code, version control (swc2126/usetailwag.co) |

# 4. 4-Day Sprint Plan

Each day builds on the previous. The staging URL is used for all testing until Day 4, when the live domain is switched.

Day 1: Scaffold & Infrastructure  —  March 26 (Thu)   [COMPLETE]

Set up the project skeleton, connect all services, and get the marketing site serving from Render on a staging URL.

| Task | Status | Notes |
| --- | --- | --- |
| Create Node.js + Express project in GitHub repo | Done | server.js, package.json, /public folder |
| Create Render Web Service (connect to GitHub) | Done | Auto-deploys on push to main |
| Create Supabase project | Done | Save project URL + anon key |
| Create database tables (users, daycares, subscriptions) | Done | Via Supabase SQL editor |
| Move marketing site HTML to /public | Done | index.html + all assets |
| Verify marketing site loads on Render staging URL | Done | Should look identical to current site |
| Set up environment variables on Render | Done | SUPABASE_URL, STRIPE_KEY, etc. |

Day 2: Auth & Payments  —  March 27 (Fri)   [COMPLETE]

Wire up real user authentication and Stripe Checkout so a user can sign up, choose a plan, pay, and land on a dashboard.

| Task | Status | Notes |
| --- | --- | --- |
| Connect signup page to Supabase Auth | Done | Email + password registration |
| Connect login page to Supabase Auth | Done | Session tokens, redirect to dashboard |
| Create Stripe Checkout session endpoint | Done | POST /api/create-checkout-session |
| Configure Stripe products + prices | Done | Starter/Growth/Pro, quarterly/annual |
| Handle Stripe webhook for payment success | Done | POST /api/webhook — update subscription status |
| Create basic dashboard page (post-login) | Done | Welcome screen, plan info |
| Test full signup → pay → dashboard flow | Done | Use Stripe test mode |

Day 3: Dashboard & Polish  —  March 28 (Sat)   [NOT STARTED]

Build out the dashboard, handle edge cases, test on mobile, and prepare for the domain switch.

| Task | Status | Notes |
| --- | --- | --- |
| Build dashboard with daycare info + plan status | Pending | Matching TailWag brand |
| Add logout functionality | Pending | Clear session, redirect to homepage |
| Add password reset flow | Pending | Via Supabase magic link email |
| Handle auth guards (protect dashboard routes) | Pending | Redirect unauthenticated users to login |
| Mobile responsive testing | Pending | All pages, all breakpoints |
| Error handling (invalid login, payment failures) | Pending | User-friendly error messages |
| End-to-end test: full user journey | Pending | Signup → pay → dashboard → logout → login |

Day 4: Domain Migration & Go-Live  —  March 29 (Sun)   [NOT STARTED]

Switch the live domain from GitHub Pages to Render. Verify everything works. Celebrate.

| Task | Status | Notes |
| --- | --- | --- |
| Add custom domain to Render | Pending | usetailwag.co in Render dashboard |
| Update Namecheap DNS records | Pending | Change A records or add CNAME to Render |
| Wait for DNS propagation | Pending | Typically 5–30 minutes |
| Verify site loads on usetailwag.co | Pending | Check all pages + SSL |
| Test full flow on live domain | Pending | Signup, login, Stripe, dashboard |
| Update Stripe webhook URL to production domain | Pending | In Stripe dashboard |
| Remove GitHub Pages configuration (optional) | Pending | Can keep as backup initially |

# 5. Phase 1 Detail: Scaffold & Infrastructure

### Project Structure

The app will be organized as follows in the GitHub repository:

usetailwag.co/

├── server.js              # Express entry point

├── package.json           # Dependencies

├── .env                   # Local env vars (not committed)

├── /public                # Static files (marketing site)

│   ├── index.html         # Marketing homepage

│   ├── login.html         # Login page

│   ├── signup.html        # Signup + payment page

│   └── dashboard.html     # Post-login dashboard

├── /routes                # Express API routes

│   ├── auth.js            # Auth endpoints

│   └── stripe.js          # Payment endpoints + webhook

└── /config                # Supabase + Stripe config

### Environment Variables Required

| Variable | Description |
| --- | --- |
| SUPABASE_URL |  | Your Supabase project URL (from project settings) |
| SUPABASE_ANON_KEY |  | Supabase anonymous/public key |
| SUPABASE_SERVICE_KEY |  | Supabase service role key (server-side only) |
| STRIPE_SECRET_KEY |  | Stripe secret key (sk_test_... or sk_live_...) |
| STRIPE_PUBLISHABLE_KEY |  | Stripe publishable key (pk_test_... or pk_live_...) |
| STRIPE_WEBHOOK_SECRET |  | Stripe webhook signing secret (whsec_...) |
| NODE_ENV |  | Set to ‘production’ on Render |
| PORT |  | Auto-set by Render (usually 10000) |

### Render Setup Steps

- Go to render.com and create an account (or sign in with GitHub)

- Click "New" → "Web Service"

- Connect your GitHub account and select the swc2126/usetailwag.co repository

- Set Build Command: npm install

- Set Start Command: node server.js

- Choose "Free" plan to start (can upgrade later)

- Add environment variables in the "Environment" tab

# 9. Troubleshooting Guide

Common issues encountered during this migration and how to resolve them:

### Render deploy fails

- Check the deploy log in the Render dashboard for specific errors

- Ensure package.json has a valid "start" script: "node server.js"

- Verify all environment variables are set (missing vars cause crashes)

### Supabase auth not working

- Check that SUPABASE_URL and SUPABASE_ANON_KEY are correct in Render env vars

- In Supabase dashboard → Authentication → URL Configuration: add your Render URL and production domain as allowed redirect URLs

- Email confirmation is enabled by default — disable it in Supabase Auth settings during development

### Stripe payments not processing

- Confirm you’re using test mode keys (sk_test_... and pk_test_...) during development

- Stripe webhook must point to your Render URL: https://your-app.onrender.com/api/webhook

- Webhook signing secret (STRIPE_WEBHOOK_SECRET) must match the one in Stripe dashboard

### DNS not resolving after migration

- DNS propagation can take 5–30 minutes (occasionally up to 48 hours for some ISPs)

- Use dnschecker.org to verify your A record or CNAME is propagating

- Remove the old GitHub Pages CNAME file from the repo to avoid conflicts

- Ensure SSL certificate is issued in Render dashboard (auto-provisions with Let’s Encrypt)

### Site loads but login/signup doesn’t work

- Open browser DevTools (F12) → Console tab to see JavaScript errors

- Check the Network tab for failed API requests (red entries)

- Verify the API base URL in your frontend code matches the Render deployment URL

# 10. Post-Launch Checklist

After the domain is switched and everything is verified working:

- Switch Stripe from test mode to live mode (swap API keys in Render env vars)

- Create live Stripe webhook pointing to production domain

- Enable email confirmation in Supabase Auth for production

- Set up Supabase email templates (branded confirmation + password reset emails)

- Test a real payment end-to-end with a live card

- Consider upgrading Render to a paid plan for faster cold starts and always-on

- Archive the GitHub Pages setup (remove CNAME file, disable Pages in repo settings)

- Set up monitoring / uptime alerts (Render provides basic health checks)

# 11. Change Log

This log tracks all significant actions taken during the migration.

| Date | Action | Status |
| --- | --- | --- |
| Mar 26 | Project documentation created. Architecture decision made: Render + Supabase + Stripe. 4-day sprint plan finalized. | Done |
| Mar 26 | login.html uploaded to GitHub repo (swc2126/usetailwag.co) | Done |
| Mar 26 | signup.html created locally (Stripe Elements, plan selector, TailWag brand). Not yet uploaded to GitHub. | Partial |
| Mar 26 | Decision: Pivot from GitHub Pages to Render + Supabase. GitHub Pages is static-only; TailWag needs auth, database, and payments. | Done |
| Mar 26 | Day 1 complete. Node.js + Express app scaffolded. Marketing site serving from Render at https://usetailwag-co.onrender.com. Project structure: server.js, /public, /routes, /config. Supabase project created. Stripe test mode configured. Exposed API keys rotated and TailWag_Session_Context.txt removed from git history. | Done |
| Mar 26 | Day 2 complete. Supabase Auth wired up (signup, login, session management). Stripe Checkout integrated with 6 auto-created prices (Starter/Growth/Pro x Quarterly/Annual). Webhook handling for checkout.session.completed, subscription.updated, subscription.deleted. Dashboard shows user profile, daycare info, and subscription status. Auth guard protects dashboard. Full signup-pay-dashboard flow tested end-to-end on production. | Done |

(This log will be updated as each phase is completed.)